## Issues
Issue Key | Theme | WorkStream | TAGS | Summary | Issue Type | Parent Key | Status | Priority | Reporter | Assignee | Start Date | Due Date | Sprint | Fix Version | Original Estimate (days) | Story Points | Project | Dependencies | Milestone | Risk Level | Risk Description | Risk Due Date | Risk Owner | Historical Accuracy | Complexity Score | Business Value
PSSDP- 1121 | Programme | Platform | POD1 | Sample issue summary 1 | Initiative |  | In Progress | High | Heidi | Divya | 2025-03-26 | 2025-07-30 |  |  |  | 3 | Lucid | PSSDP- 1130, PSSDP- 1154 | FALSE |  |  |  |  | 0.71 | 2 | 10
PSSDP- 1122 | Programme | Platform | POD2 | Sample issue summary 2 | Initiative |  | In Progress | Medium | Eve | Divya | 2025-05-02 | 2025-08-31 |  |  |  | 13 | Snowflake | PSSDP- 1124, PSSDP- 1147 | FALSE |  |  |  |  | 1.07 | 10 | 3
PSSDP- 1123 | Programme | Platform | POD2 | Sample issue summary 2 | Epic | PSSDP- 1122 | In Progress | Medium | Eve | Shane | 2025-05-05 | 2025-06-30 |  |  |  | 13 | Snowflake |  | FALSE |  |  |  |  | 1.16 | 3 | 4
PSSDP- 1124 | Programme | Platform | POD1 | Sample issue summary 3 | Epic | PSSDP- 1121 | In Progress | High | Heidi | Shane | 2025-03-27 | 2025-05-07 |  |  |  | 13 | Lucid | PSSDP- 1158, PSSDP- 1144, PSSDP- 1161 | FALSE |  |  |  |  | 0.97 | 8 | 9
PSSDP- 1125 | Programme | Platform | POD1 | Sample issue summary 4 | Epic | PSSDP- 1121 | To Do | High | Heidi | Shane | 2025-05-08 | 2025-07-31 |  |  |  | 13 | Lucid |  | FALSE | Low | Some technical debt accumulation possible | 2025-07-23 | Alice | 0.78 | 8 | 4
PSSDP- 1126 | Programme | Platform | POD1 | Sample issue summary 5 | Story | PSSDP- 1121 | Done | High | Heidi | Shane | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid | PSSDP- 1121 | FALSE | Medium | Resource allocation conflicts with other project | 2025-03-30 | Shane | 1.06 | 5 | 6
PSSDP- 1127 | Programme | Platform | POD1 | Sample issue summary 5 | Story | PSSDP- 1124 | Done | High | Heidi | Bob | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid | PSSDP- 1158 | FALSE | Medium | Resource allocation conflicts with other project | 2025-04-06 | Charlie | 1.25 | 5 | 4
PSSDP- 1128 | Programme | Platform | POD1 | Sample issue summary 6 | Story | PSSDP- 1124 | Done | Medium | Heidi | Mark | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid |  | FALSE | Medium | Resource allocation conflicts with other project | 2025-03-29 | Shane | 1.25 | 10 | 9
PSSDP- 1129 | Programme | Platform | POD1 | Sample issue summary 7 | Story | PSSDP- 1124 | Done | High | Eve | Julie | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid |  | TRUE |  |  |  |  | 0.94 | 5 | 6
PSSDP- 1130 | Programme | Platform | POD1 | Sample issue summary 8 | Story | PSSDP- 1124 | Done | Low | Heidi | Diana | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 5 | 5 | Lucid | PSSDP- 1148 | FALSE | Medium | Integration with third-party API could be unstable | 2025-03-30 | Shane | 0.69 | 2 | 6
PSSDP- 1131 | Programme | Platform | POD1 | Sample issue summary 9 | Story | PSSDP- 1124 | Done | Medium | Frank | Robert | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid |  | FALSE |  |  |  |  | 1.04 | 10 | 2
PSSDP- 1132 | Programme | Platform | POD1 | Sample issue summary 10 | Story | PSSDP- 1124 | Done | Medium | Grace | Alice | 2024-04-21 | 2025-04-23 | Sprint 1 | v1.0 | 3 | 3 | Lucid | PSSDP- 1161, PSSDP- 1158 | FALSE | Medium | Resource allocation conflicts with other project | 2025-04-18 | Julie | 1.18 | 6 | 10
PSSDP- 1133 | Programme | Platform | POD1 | Sample issue summary 11 | Story | PSSDP- 1124 | Done | Medium | Grace | Charlie | 2024-04-21 | 2025-04-23 | Sprint 1 | v1.0 | 3 | 3 | Lucid | PSSDP- 1167 | FALSE |  |  |  |  | 1.16 | 2 | 10
PSSDP- 1134 | Programme | Platform | POD1 | Sample issue summary 12 | Story | PSSDP- 1124 | Done | Medium | Eve | Diana | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid | PSSDP- 1142, PSSDP- 1137, PSSDP- 1164 | FALSE |  |  |  |  | 1.16 | 1 | 3
PSSDP- 1135 | Programme | Platform | POD1 | Sample issue summary 13 | Story | PSSDP- 1124 | Done | Medium | Grace | Julie | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid |  | FALSE |  |  |  |  | 0.88 | 3 | 8
PSSDP- 1136 | Programme | Platform | POD1 | Sample issue summary 14 | Story | PSSDP- 1124 | Done | Medium | Grace | Charlie | 2024-04-21 | 2025-04-23 | Sprint 2 | v2.0 | 3 | 3 | Lucid |  | FALSE | Low | Some technical debt accumulation possible | 2025-04-20 | Julie | 1.37 | 5 | 1
PSSDP- 1137 | Programme | Platform | POD1 | Sample issue summary 15 | Bug | PSSDP- 1124 | Done | Medium | Grace | Bob | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 2 | 2 | Lucid | PSSDP- 1126, PSSDP- 1133, PSSDP- 1156 | FALSE |  |  |  |  | 1.07 | 8 | 5
PSSDP- 1138 | Programme | Platform | POD1 | Sample issue summary 16 | Story | PSSDP- 1124 | Done | High | Eve | Mark | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid | PSSDP- 1145 | FALSE | Low | Slight learning curve for new technology | 2025-04-12 | Alice | 1.16 | 3 | 4
PSSDP- 1139 | Programme | Platform | POD1 | Sample issue summary 17 | Story | PSSDP- 1124 | Done | Medium | Frank | Robert | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid | PSSDP- 1132, PSSDP- 1129 | TRUE |  |  |  |  | 1.16 | 4 | 2
PSSDP- 1140 | Programme | Platform | POD1 | Sample issue summary 18 | Story | PSSDP- 1124 | Done | Medium | Frank | Shane | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 3 | 3 | Lucid | PSSDP- 1151 | FALSE |  |  |  |  | 1.25 | 3 | 8
PSSDP- 1141 | Programme | Platform | POD1 | Sample issue summary 19 | Story | PSSDP- 1124 | In Progress | Critical | Grace | Mark | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid | PSSDP- 1138, PSSDP- 1165, PSSDP- 1153 | TRUE | Medium | Performance testing reveals borderline metrics | 2025-05-03 | Julie | 0.71 | 9 | 9
PSSDP- 1142 | Programme | Platform | POD1 | Sample issue summary 20 | Story | PSSDP- 1124 | In Progress | Medium | Grace | Diana | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid |  | FALSE |  |  |  |  | 0.87 | 2 | 6
PSSDP- 1143 | Programme | Platform | POD1 | Sample issue summary 21 | Story | PSSDP- 1124 | In Progress | Medium | Grace | Julie | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid | PSSDP- 1159 | TRUE |  |  |  |  | 1.2 | 4 | 6
PSSDP- 1144 | Programme | Platform | POD1 | Sample issue summary 22 | Story | PSSDP- 1124 | In Progress | Medium | Eve | Bob | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid |  | FALSE | Medium | Resource allocation conflicts with other project | 2025-04-28 | Alice | 0.84 | 1 | 2
PSSDP- 1145 | Programme | Platform | POD1 | Sample issue summary 23 | Story | PSSDP- 1124 | Backlog | Medium | Heidi | Diana | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid | PSSDP- 1144, PSSDP- 1167 | TRUE |  |  |  |  | 1.37 | 3 | 3
PSSDP- 1146 | Programme | Platform | POD1 | Sample issue summary 24 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Alice | 2025-05-05 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid |  | FALSE | High | Key subject matter expert has limited availability | 2025-04-27 | Diana | 0.99 | 1 | 6
PSSDP- 1147 | Programme | Platform | POD1 | Sample issue summary 25 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Charlie | 2025-05-05 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid | PSSDP- 1128 | FALSE |  |  |  |  | 0.9 | 8 | 5
PSSDP- 1148 | Programme | Platform | POD1 | Sample issue summary 26 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Robert | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid |  | TRUE |  |  |  |  | 1.11 | 7 | 4
PSSDP- 1149 | Programme | Platform | POD1 | Sample issue summary 27 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Shane | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 2 | 2 | Lucid | PSSDP- 1141 | FALSE |  |  |  |  | 0.89 | 1 | 6
PSSDP- 1150 | Programme | Platform | POD1 | Sample issue summary 28 | Story | PSSDP- 1125 | Backlog | High | Grace | Bob | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid |  | FALSE |  |  |  |  | 0.66 | 3 | 10
PSSDP- 1151 | Programme | Platform | POD1 | Sample issue summary 29 | Story | PSSDP- 1125 | Backlog | Medium | Grace | Diana | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid | PSSDP- 1165, PSSDP- 1121 | FALSE |  |  |  |  | 0.66 | 1 | 1
PSSDP- 1152 | Programme | Platform | POD1 | Sample issue summary 30 | Story | PSSDP- 1125 | Backlog | Medium | Grace | Julie | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid | PSSDP- 1137, PSSDP- 1158, PSSDP- 1150 | FALSE |  |  |  |  | 1.32 | 1 | 7
PSSDP- 1153 | Programme | Platform | POD1 | Sample issue summary 31 | Story | PSSDP- 1125 | Backlog | Medium | Eve | Bob | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid | PSSDP- 1130 | FALSE |  |  |  |  | 0.68 | 7 | 2
PSSDP- 1154 | Programme | Platform | POD1 | Sample issue summary 32 | Story | PSSDP- 1125 | Backlog | Medium | Heidi | Mark | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid |  | FALSE | Critical | Security vulnerability identified in core component | 2025-05-12 | Bob | 0.81 | 2 | 1
PSSDP- 1155 | Programme | Platform | POD1 | Sample issue summary 33 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Alice | 2025-05-19 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid |  | FALSE | High | Technical approach has significant uncertainties | 2025-05-11 | Shane | 0.76 | 9 | 7
PSSDP- 1156 | Programme | Platform | POD1 | Sample issue summary 34 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Charlie | 2025-05-19 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid | PSSDP- 1124, PSSDP- 1154, PSSDP- 1146 | FALSE | Medium | Resource allocation conflicts with other project | 2025-05-10 | Alice | 0.75 | 4 | 2
PSSDP- 1157 | Programme | Platform | POD1 | Sample issue summary 35 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Robert | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid |  | FALSE | Medium | Resource allocation conflicts with other project | 2025-05-13 | Mark | 0.95 | 3 | 7
PSSDP- 1158 | Programme | Platform | POD1 | Sample issue summary 36 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Shane | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid |  | FALSE |  |  |  |  | 1.12 | 2 | 10
PSSDP- 1159 | Programme | Platform | POD2 | Sample issue summary 28 | Story | PSSDP- 1123 | Backlog | High | Grace | Bob | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake |  | FALSE |  |  |  |  | 0.6 | 5 | 7
PSSDP- 1160 | Programme | Platform | POD2 | Sample issue summary 29 | Story | PSSDP- 1123 | Backlog | Medium | Grace | Diana | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake |  | FALSE |  |  |  |  | 1.27 | 1 | 7
PSSDP- 1161 | Programme | Platform | POD2 | Sample issue summary 30 | Story | PSSDP- 1123 | Backlog | Medium | Grace | Julie | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake |  | FALSE | Low | Minor documentation issues may delay review | 2025-05-06 | Julie | 1.21 | 7 | 5
PSSDP- 1162 | Programme | Platform | POD2 | Sample issue summary 31 | Story | PSSDP- 1123 | Backlog | Medium | Eve | Bob | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake |  | TRUE |  |  |  |  | 1.3 | 3 | 7
PSSDP- 1163 | Programme | Platform | POD2 | Sample issue summary 32 | Story | PSSDP- 1123 | Backlog | Medium | Heidi | Mark | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake | PSSDP- 1139, PSSDP- 1154, PSSDP- 1129 | FALSE |  |  |  |  | 0.86 | 6 | 6
PSSDP- 1164 | Programme | Platform | POD2 | Sample issue summary 33 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Alice | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake | PSSDP- 1126 | FALSE |  |  |  |  | 1.35 | 5 | 7
PSSDP- 1165 | Programme | Platform | POD2 | Sample issue summary 34 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Charlie | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake |  | TRUE |  |  |  |  | 1 | 9 | 5
PSSDP- 1166 | Programme | Platform | POD2 | Sample issue summary 35 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Robert | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake |  | FALSE |  |  |  |  | 0.92 | 7 | 6
PSSDP- 1167 | Programme | Platform | POD2 | Sample issue summary 36 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Shane | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake | PSSDP- 1146, PSSDP- 1164 | FALSE |  |  |  |  | 0.79 | 4 | 8

## Skills
Resource | Skillset | Proficiency | Secondary Skills | Velocity Factor | Cost Rate
Alice | QA | 4 | Tech Lead | 0.83 | 68
Charlie | QA | 3 |  | 0.77 | 64
Diana | Dev | 4 | QA, PM | 1.2 | 115
Bob | Dev | 5 | QA, PM | 0.93 | 118
Mark | Dev | 5 |  | 1.08 | 67
Julie | Dev | 2 | Tech Lead, PM | 0.76 | 57
Robert | DevOps | 2 | Dev | 1.13 | 105
Shane | Tech Lead | 4 | PM, DevOps | 1.06 | 75
Divya | PM | 5 | QA | 1.29 | 123

## Worklogs
Issue Key | Resource | Date | Time Spent (hrs)
PSSDP- 1121 | Divya | 2025-04-03 | 4
PSSDP- 1122 | Divya | 2025-05-12 | 8
PSSDP- 1122 | Divya | 2025-05-02 | 6
PSSDP- 1122 | Divya | 2025-05-07 | 8
PSSDP- 1123 | Shane | 2025-05-13 | 2
PSSDP- 1124 | Shane | 2025-04-03 | 8
PSSDP- 1125 | Shane | 2025-05-17 | 2
PSSDP- 1126 | Shane | 2025-04-05 | 6
PSSDP- 1126 | Shane | 2025-04-06 | 2
PSSDP- 1126 | Shane | 2025-04-05 | 8
PSSDP- 1127 | Bob | 2025-03-27 | 8
PSSDP- 1128 | Mark | 2025-04-04 | 4
PSSDP- 1128 | Mark | 2025-04-06 | 4
PSSDP- 1128 | Mark | 2025-03-29 | 4
PSSDP- 1129 | Julie | 2025-03-28 | 2
PSSDP- 1130 | Diana | 2025-04-01 | 6
PSSDP- 1130 | Diana | 2025-04-04 | 8
PSSDP- 1130 | Diana | 2025-03-31 | 4
PSSDP- 1131 | Robert | 2025-03-31 | 4
PSSDP- 1131 | Robert | 2025-04-04 | 2
PSSDP- 1131 | Robert | 2025-03-29 | 2
PSSDP- 1132 | Alice | 2024-04-29 | 6
PSSDP- 1132 | Alice | 2024-04-23 | 8
PSSDP- 1133 | Charlie | 2024-04-30 | 8
PSSDP- 1133 | Charlie | 2024-04-24 | 4
PSSDP- 1133 | Charlie | 2024-04-30 | 4
PSSDP- 1134 | Diana | 2025-04-13 | 6
PSSDP- 1135 | Julie | 2025-04-17 | 4
PSSDP- 1136 | Charlie | 2024-04-25 | 8
PSSDP- 1136 | Charlie | 2024-04-24 | 8
PSSDP- 1137 | Bob | 2025-04-17 | 4
PSSDP- 1137 | Bob | 2025-04-19 | 4
PSSDP- 1138 | Mark | 2025-04-20 | 8
PSSDP- 1139 | Robert | 2025-04-15 | 8
PSSDP- 1139 | Robert | 2025-04-14 | 2
PSSDP- 1139 | Robert | 2025-04-10 | 6
PSSDP- 1140 | Shane | 2025-04-11 | 8
PSSDP- 1140 | Shane | 2025-04-12 | 8
PSSDP- 1140 | Shane | 2025-04-19 | 6
PSSDP- 1141 | Mark | 2025-04-28 | 6
PSSDP- 1142 | Diana | 2025-04-25 | 8
PSSDP- 1142 | Diana | 2025-05-01 | 2
PSSDP- 1143 | Julie | 2025-05-04 | 8
PSSDP- 1143 | Julie | 2025-05-02 | 2
PSSDP- 1143 | Julie | 2025-05-02 | 4
PSSDP- 1144 | Bob | 2025-04-27 | 8
PSSDP- 1144 | Bob | 2025-05-02 | 8
PSSDP- 1144 | Bob | 2025-04-30 | 2
PSSDP- 1145 | Diana | 2025-05-01 | 2
PSSDP- 1146 | Alice | 2025-05-14 | 4
PSSDP- 1147 | Charlie | 2025-05-10 | 2
PSSDP- 1147 | Charlie | 2025-05-07 | 8
PSSDP- 1147 | Charlie | 2025-05-05 | 2
PSSDP- 1148 | Robert | 2025-04-28 | 2
PSSDP- 1149 | Shane | 2025-04-27 | 8
PSSDP- 1149 | Shane | 2025-04-24 | 2
PSSDP- 1149 | Shane | 2025-04-26 | 8
PSSDP- 1150 | Bob | 2025-05-09 | 8
PSSDP- 1150 | Bob | 2025-05-15 | 2
PSSDP- 1151 | Diana | 2025-05-08 | 8
PSSDP- 1152 | Julie | 2025-05-15 | 4
PSSDP- 1152 | Julie | 2025-05-10 | 2
PSSDP- 1152 | Julie | 2025-05-10 | 4
PSSDP- 1153 | Bob | 2025-05-14 | 6
PSSDP- 1154 | Mark | 2025-05-11 | 2
PSSDP- 1154 | Mark | 2025-05-10 | 2
PSSDP- 1155 | Alice | 2025-05-23 | 2
PSSDP- 1155 | Alice | 2025-05-24 | 6
PSSDP- 1156 | Charlie | 2025-05-26 | 4
PSSDP- 1156 | Charlie | 2025-05-21 | 6
PSSDP- 1157 | Robert | 2025-05-09 | 2
PSSDP- 1158 | Shane | 2025-05-15 | 2
PSSDP- 1158 | Shane | 2025-05-14 | 2
PSSDP- 1159 | Bob | 2025-05-08 | 6
PSSDP- 1159 | Bob | 2025-05-06 | 8
PSSDP- 1159 | Bob | 2025-05-05 | 6
PSSDP- 1160 | Diana | 2025-05-06 | 4
PSSDP- 1160 | Diana | 2025-05-12 | 4
PSSDP- 1161 | Julie | 2025-05-07 | 8
PSSDP- 1161 | Julie | 2025-05-13 | 2
PSSDP- 1162 | Bob | 2025-05-13 | 6
PSSDP- 1162 | Bob | 2025-05-11 | 4
PSSDP- 1163 | Mark | 2025-05-05 | 8
PSSDP- 1163 | Mark | 2025-05-08 | 4
PSSDP- 1163 | Mark | 2025-05-13 | 2
PSSDP- 1164 | Alice | 2025-05-09 | 8
PSSDP- 1165 | Charlie | 2025-05-05 | 8
PSSDP- 1165 | Charlie | 2025-05-09 | 6
PSSDP- 1166 | Robert | 2025-05-13 | 4
PSSDP- 1167 | Shane | 2025-05-12 | 2
PSSDP- 1167 | Shane | 2025-05-14 | 4

## Non_Availability
Start Date | End Date | Resource | Reason
2025-05-06 | 2025-05-09 | Alice | Sick
2025-04-24 | 2025-04-27 | Charlie | Training
2025-05-15 | 2025-05-18 | Diana | Training
2025-05-06 | 2025-05-09 | Diana | Holiday
2025-04-17 | 2025-04-20 | Bob | Training
2025-05-12 | 2025-05-15 | Mark | Holiday
2025-05-02 | 2025-05-05 | Julie | Holiday
2025-05-11 | 2025-05-14 | Julie | Training
2025-05-12 | 2025-05-15 | Robert | Leave
2025-04-28 | 2025-05-01 | Shane | Sick
2025-05-01 | 2025-05-04 | Shane | Training
2025-05-11 | 2025-05-14 | Divya | Sick

## Task Dependencies
Source Task | Dependent Task | Dependency Type | Delay Impact (days)
PSSDP- 1130 | PSSDP- 1121 | Finish-to-Finish | 7
PSSDP- 1154 | PSSDP- 1121 | Finish-to-Start | 3
PSSDP- 1124 | PSSDP- 1122 | Finish-to-Start | 5
PSSDP- 1147 | PSSDP- 1122 | Start-to-Start | 4
PSSDP- 1158 | PSSDP- 1124 | Finish-to-Start | 6
PSSDP- 1144 | PSSDP- 1124 | Finish-to-Start | 1
PSSDP- 1161 | PSSDP- 1124 | Finish-to-Start | 9
PSSDP- 1121 | PSSDP- 1126 | Start-to-Start | 6
PSSDP- 1158 | PSSDP- 1127 | Finish-to-Start | 9
PSSDP- 1148 | PSSDP- 1130 | Finish-to-Start | 4
PSSDP- 1161 | PSSDP- 1132 | Finish-to-Start | 1
PSSDP- 1158 | PSSDP- 1132 | Finish-to-Start | 8
PSSDP- 1167 | PSSDP- 1133 | Finish-to-Start | 8
PSSDP- 1142 | PSSDP- 1134 | Finish-to-Start | 2
PSSDP- 1137 | PSSDP- 1134 | Finish-to-Start | 6
PSSDP- 1164 | PSSDP- 1134 | Start-to-Start | 6
PSSDP- 1126 | PSSDP- 1137 | Finish-to-Start | 3
PSSDP- 1133 | PSSDP- 1137 | Finish-to-Start | 2
PSSDP- 1156 | PSSDP- 1137 | Finish-to-Start | 6
PSSDP- 1145 | PSSDP- 1138 | Finish-to-Start | 3
PSSDP- 1132 | PSSDP- 1139 | Finish-to-Start | 8
PSSDP- 1129 | PSSDP- 1139 | Finish-to-Start | 4
PSSDP- 1151 | PSSDP- 1140 | Finish-to-Start | 6
PSSDP- 1138 | PSSDP- 1141 | Finish-to-Start | 8
PSSDP- 1165 | PSSDP- 1141 | Start-to-Start | 8
PSSDP- 1153 | PSSDP- 1141 | Finish-to-Start | 1
PSSDP- 1159 | PSSDP- 1143 | Finish-to-Start | 8
PSSDP- 1144 | PSSDP- 1145 | Start-to-Start | 7
PSSDP- 1167 | PSSDP- 1145 | Finish-to-Finish | 1
PSSDP- 1128 | PSSDP- 1147 | Start-to-Start | 3
PSSDP- 1141 | PSSDP- 1149 | Finish-to-Start | 6
PSSDP- 1165 | PSSDP- 1151 | Finish-to-Finish | 7
PSSDP- 1121 | PSSDP- 1151 | Start-to-Start | 2
PSSDP- 1137 | PSSDP- 1152 | Finish-to-Start | 6
PSSDP- 1158 | PSSDP- 1152 | Finish-to-Start | 9
PSSDP- 1150 | PSSDP- 1152 | Start-to-Start | 9
PSSDP- 1130 | PSSDP- 1153 | Finish-to-Start | 9
PSSDP- 1124 | PSSDP- 1156 | Finish-to-Start | 3
PSSDP- 1154 | PSSDP- 1156 | Start-to-Start | 9
PSSDP- 1146 | PSSDP- 1156 | Finish-to-Start | 5
PSSDP- 1139 | PSSDP- 1163 | Start-to-Start | 2
PSSDP- 1154 | PSSDP- 1163 | Finish-to-Start | 7
PSSDP- 1129 | PSSDP- 1163 | Finish-to-Start | 4
PSSDP- 1126 | PSSDP- 1164 | Finish-to-Start | 7
PSSDP- 1146 | PSSDP- 1167 | Start-to-Start | 6
PSSDP- 1164 | PSSDP- 1167 | Finish-to-Start | 5

## Velocity History
Sprint | Team Member | Points Committed | Points Completed | Completion Rate
Sprint 1 | Alice | 14 | 9 | 0.64
Sprint 1 | Charlie | 16 | 12 | 0.75
Sprint 1 | Diana | 7 | 5 | 0.71
Sprint 1 | Bob | 11 | 9 | 0.82
Sprint 1 | Mark | 18 | 15 | 0.83
Sprint 1 | Julie | 19 | 17 | 0.89
Sprint 1 | Robert | 10 | 9 | 0.9
Sprint 1 | Shane | 17 | 13 | 0.76
Sprint 1 | Divya | 15 | 10 | 0.67
Sprint 2 | Alice | 16 | 15 | 0.94
Sprint 2 | Charlie | 11 | 9 | 0.82
Sprint 2 | Diana | 18 | 17 | 0.94
Sprint 2 | Bob | 14 | 13 | 0.93
Sprint 2 | Mark | 13 | 13 | 1
Sprint 2 | Julie | 8 | 7 | 0.88
Sprint 2 | Robert | 16 | 17 | 1.06
Sprint 2 | Shane | 11 | 10 | 0.91
Sprint 2 | Divya | 14 | 10 | 0.71
Sprint 3 | Alice | 5 | 3 | 0.6
Sprint 3 | Charlie | 8 | 5 | 0.62
Sprint 3 | Diana | 16 | 16 | 1
Sprint 3 | Bob | 11 | 11 | 1
Sprint 3 | Mark | 17 | 16 | 0.94
Sprint 3 | Julie | 15 | 14 | 0.93
Sprint 3 | Robert | 11 | 9 | 0.82
Sprint 3 | Shane | 14 | 14 | 1
Sprint 3 | Divya | 19 | 15 | 0.79
Sprint 4 | Alice | 12 | 11 | 0.92
Sprint 4 | Charlie | 18 | 17 | 0.94
Sprint 4 | Diana | 9 | 6 | 0.67
Sprint 4 | Bob | 6 | 4 | 0.67
Sprint 4 | Mark | 20 | 17 | 0.85
Sprint 4 | Julie | 12 | 12 | 1
Sprint 4 | Robert | 5 | 5 | 1
Sprint 4 | Shane | 11 | 8 | 0.73
Sprint 4 | Divya | 19 | 14 | 0.74
Sprint 5 | Alice | 14 | 11 | 0.79
Sprint 5 | Charlie | 19 | 16 | 0.84
Sprint 5 | Diana | 16 | 17 | 1.06
Sprint 5 | Bob | 9 | 8 | 0.89
Sprint 5 | Mark | 16 | 13 | 0.81
Sprint 5 | Julie | 16 | 15 | 0.94
Sprint 5 | Robert | 14 | 10 | 0.71
Sprint 5 | Shane | 5 | 5 | 1
Sprint 5 | Divya | 16 | 17 | 1.06

## Resource Costs
Resource | Role | Cost Rate | Time Allocation | Start Date | End Date
Alice | QA | 68 | 1 | 2025-03-03 13:46 | 2025-06-26 13:46
Charlie | QA | 64 | 0.75 | 2025-02-06 13:46 | 2025-07-05 13:46
Diana | UX Designer | 115 | 1 | 2025-03-10 13:46 | 2025-06-16 13:46
Bob | Architect | 118 | 0.75 | 2025-02-22 13:46 | 2025-07-16 13:46
Mark | Architect | 67 | 0.5 | 2025-02-08 13:46 | 2025-07-29 13:46
Julie | Architect | 57 | 0.75 | 2025-03-19 13:46 | 2025-06-24 13:46
Robert | DevOps | 105 | 0.75 | 2025-03-28 13:46 | 2025-08-16 13:46
Shane | UX Designer | 75 | 0.75 | 2025-04-03 13:46 | 2025-07-30 13:46
Divya | Scrum Master | 123 | 0.5 | 2025-02-10 13:46 | 2025-08-01 13:46

## Technical Debt
ID | Description | Category | Impact Level | Estimated Resolution Time (days) | Created Date | Target Resolution Date | Owner | Status
TD-001 | Test coverage below 60% for core modules | Testing | Low | 8 | 2025-02-23 13:46 | 2025-04-05 13:46 | Shane | Resolved
TD-002 | Credentials in source code | Security | Low | 4 | 2025-03-26 13:46 | 2025-07-06 13:46 | Robert | Open
TD-003 | API documentation out of date | Documentation | Medium | 6 | 2025-01-28 13:46 | 2025-05-09 13:46 | Charlie | Open
TD-004 | Deployment process poorly documented | Documentation | Medium | 10 | 2025-02-24 13:46 | 2025-05-06 13:46 | Bob | Open
TD-005 | Insufficient input validation | Security | Medium | 14 | 2025-04-06 13:46 | 2025-06-23 13:46 | Robert | Open
TD-006 | Credentials in source code | Security | Medium | 1 | 2025-03-20 13:46 | 2025-05-04 13:46 | Alice | Open
TD-007 | Missing architectural decision records | Documentation | Low | 8 | 2025-03-10 13:46 | 2025-04-25 13:46 | Robert | In Progress
TD-008 | Manual deployment process prone to errors | Infrastructure | Low | 2 | 2025-03-30 13:46 | 2025-07-13 13:46 | Shane | Open
TD-009 | Monolithic design limiting scalability | Architecture | Medium | 16 | 2025-02-13 13:46 | 2025-04-07 13:46 | Bob | In Progress
TD-010 | High cyclomatic complexity in authentication module | Code Quality | Low | 18 | 2025-04-24 13:46 | 2025-06-29 13:46 | Shane | Open
TD-011 | Development and staging environments not matching production | Infrastructure | Medium | 19 | 2025-04-07 13:46 | 2025-06-08 13:46 | Divya | Open
TD-012 | Insufficient input validation | Security | Medium | 4 | 2025-01-26 13:46 | 2025-02-28 13:46 | Shane | Open
TD-013 | Manual deployment process prone to errors | Infrastructure | Medium | 4 | 2025-03-24 13:46 | 2025-05-18 13:46 | Alice | In Progress
TD-014 | Insufficient input validation | Security | Medium | 19 | 2025-03-06 13:46 | 2025-05-02 13:46 | Diana | Open
TD-015 | Legacy code has no unit tests | Code Quality | High | 9 | 2025-03-02 13:46 | 2025-06-12 13:46 | Charlie | In Progress